## Host Buildout Tracker
Phase | Step | What Is Being Done | Run From | Target | What To Do (Command) | Expected Result | Actual Result | Rating
PHASE 0 - PRE-FLIGHT
P0 | 0.1 | PowerCLI baseline installed | admin-pc | admin-pc | .\ESXI\Install-PowerCLIBaseline.ps1 | PowerCLI present; CEIP off
P0 | 0.2 | Connect to vCenter | admin-pc | vc01 | Connect-VIServer vc01.lab.local | Connected
PHASE 1 - CLUSTER + HOSTS
P1 | 1.1 | Create HA/DRS cluster | admin-pc | vc01 | New-Cluster -Name Cluster-A -HAEnabled -DrsEnabled | Cluster exists, HA+DRS on
P1 | 1.2 | Add hosts | admin-pc | esx01-04 | Add-VMHost per host | All hosts Connected
P1 | 1.3 | NTP configured + running | admin-pc | esx01-04 | .\ESXI\Verify-NTP.ps1 | ntpd running, policy on
PHASE 2 - NETWORKING
P2 | 2.1 | Create distributed switch | admin-pc | vc01 | .\Networking\Create-VDS.ps1 | vds-prod created, MTU 9000
P2 | 2.2 | Create portgroups + teaming | admin-pc | vc01 | .\Networking\Create-PortGroups.ps1 | Portgroups + uplink policy set
P2 | 2.3 | vMotion VMkernels | admin-pc | esx01-04 | .\ESXI\Create-Vmotion.ps1 | vMotion vmk on each host
PHASE 3 - STORAGE
P3 | 3.1 | HBA / LUN visibility | admin-pc | esx01-04 | .\ESXI\Get-HBAs.ps1 ; .\ESXI\Get-ScsiLun.ps1 | Expected HBAs + LUNs present
P3 | 3.2 | Datastores mounted on all hosts | admin-pc | Cluster-A | Get-Datastore ¦ Get-VMHost | Shared datastores on all hosts
PHASE 4 - VALIDATE
P4 | 4.1 | Host config baseline | admin-pc | esx01-04 | .\ESXI\Verify-Hosts.ps1 -InputFile hosts.txt -OutputFile baseline.csv | Baseline CSV, no anomalies
P4 | 4.2 | HA failover test | admin-pc | Cluster-A | Power off a host; observe restart | VMs restart on surviving hosts
P4 | 4.3 | vMotion test | admin-pc | Cluster-A | Move-VM test01 to another host | Live migrate, no downtime
P4 | 4.4 | Capacity + inventory snapshot | admin-pc | vc01 | .\Inventory\Get-ClusterCapacity.ps1 | Headroom + overcommit reported