## vSAN Validation Tracker
Phase | Step | What Is Being Done | Run From | Target | What To Do (Command) | Expected Result | Actual Result | Rating
PHASE 0 - PRE-FLIGHT
P0 | 0.1 | All hosts same build + vSAN-ready | admin-pc | Cluster-A | Get-VMHost ¦ Select Version,Build | Uniform build; HCL-compliant
P0 | 0.2 | Dedicated vSAN VMkernel per host | admin-pc | esx01-04 | Get-VMHostNetworkAdapter -VMKernel | vSAN vmk tagged on each host
PHASE 1 - ENABLE vSAN
P1 | 1.1 | Enable vSAN on cluster | admin-pc | Cluster-A | Set-Cluster -VsanEnabled $true | vSAN on; disk groups claimed
P1 | 1.2 | Disk groups formed (cache+capacity) | admin-pc | esx01-04 | Get-VsanDiskGroup | Disk group per host, healthy
PHASE 2 - HEALTH
P2 | 2.1 | vSAN health check all green | admin-pc | Cluster-A | Test-VsanClusterHealth / UI Skyline Health | All checks pass
P2 | 2.2 | Storage policy (FTT=1) exists + compliant | admin-pc | vc01 | Get-SpbmStoragePolicy | Default RAID-1 FTT=1 compliant
P2 | 2.3 | Capacity + slack space | admin-pc | Cluster-A | Get-VsanSpaceUsage | Adequate free + 25-30% slack
PHASE 3 - RESILIENCE
P3 | 3.1 | Host maintenance mode (ensure accessibility) | admin-pc | esx01 | Set-VMHost -State Maintenance -VsanDataMigrationMode EnsureAccessibility | Objects stay accessible
P3 | 3.2 | Simulated disk/host failure resync | admin-pc | Cluster-A | Pull a host; observe resync | Rebuild completes, FTT honored
PHASE 4 - VALIDATE
P4 | 4.1 | VM I/O during degraded state | admin-pc | Cluster-A | Run IO while 1 host down | No data loss; acceptable perf
P4 | 4.2 | Inventory snapshot | admin-pc | vc01 | .\Inventory\Get-vSphereInventory.ps1 | Datastores.csv shows vSAN capacity